| # Category | # Original Schedule | # Actual Schedule | # Originally organised by | # Actually organised by | # Content/ Remarks |
| --- | --- | --- | --- | --- | --- |
| # 1st transnational workshop on institutional support schemes/ structures | # June 2013 | # 12/ 13 September # 2013 | # HU | # HU | Overviews of and introductions to the whole institutional support schemes and structures on EU-Level and on the level of partner countries. Strengths and weaknesses of the national systems and of the European framework. Target Group: Policy Makers |
| # 2nd transnational workshop on institutional support schemes/ structures | # December 2013 | # 4 December 2013 | # DE (BMU) | # DE (BMU) | Combination of this Workshop with the Workshop on norms, standards, indicators, originally planned in October 2013 (two Workshops on two succeeding days). Overview and description of (non-financial) support schemes. Information and appetizers for small and medium sized enterprises. Target Group: Policy Makers and intermediaries |
| # Transnational workshop on Norms, standards, indicators | # October 2013 | # 5 December 2013 | # DE (BMU) | # DE (BMU) | Combination of this Workshop with the 2nd workshop on institutional support schemes/structures (two Workshops on two succeeding days). Target Group: Policy Makers and intermediaries |
| # 1st transnational workshops on issues related to Action Plan development | # January 2014 | # 7 February 2014 | # CZ | # CZ | Back to back to Tool-Training on 5/ 6 February. See programme draft from Enviros. In short: On the basis of EU and national strategies the workshop will focus on actual and possible activities on subnational , i. e. regional and municipal level. Target Group: Policy makers and intermediaries |
| # 1st transnational workshops on tools and experiences | # July 2013 | # 8 April 2014 | # IT | # DE (UBA) / BMU | EDIT Value Tool – Description, discussion and marketing. Target Group: Intermediaries |
| # 3rd transnational workshop on institutional support schemes/ structures | # May 2014 | # 3 June 2014 | # DE (BMU/ MOEZ) | # DE (BMU/ MOEZ) | Back to back to Partner Meeting on 4./ 5. June. Main focus on innovative financing schemes – different actors and framework conditions. One block on EDIT Value Tool. Target Group: Policy Makers and financial actors |
| # 2nd transnational workshops on tools and experiences | # July 2014 | # July 2014 | # DE (UBA) | # IT | EDIT Value Tool – Training and marketing. Target Group: Intermediaries |
| # 2nd transnational workshops on issues related to Action Plan development | # June 2014 | # 9 October 2014 | # DE (BMU) | # AT/ DE (MOEZ) | Financial Instruments, same focus as on 3 June. Target Group: Intermediaries and financial actors |